## Summary
Phase 5 - Sprint Summary
Sprint | Weeks | Dates | Milestone | Tasks | FE Done | BE Done | QA Passed | STG Deployed | Prod Deployed | Blocked | % Complete | Deps | External Deps | Deps Open
P5-S1 | 11-12 | 21-Sep - 02-Oct-2026 | Milestone 1 | 32 | 31 | 32 | 0 | 32 | 0 | 0 | 98.44% | 12 | 2 | 9
P5-S2 | 13-14 | 05-Oct - 16-Oct-2026 | Milestone 2 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 12 | 6 | 10
P5-S3 | 15-16 | 19-Oct - 30-Oct-2026 | Milestone 3 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 10 | 2 | 10
P5-S4 | 17-18 | 02-Nov - 13-Nov-2026 | Milestone 3 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 15 | 11 | 15
P5-S5 | 19-20 | 16-Nov - 27-Nov-2026 | Milestone 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 12 | 5 | 10
P5-S6 | 21-22 | 30-Nov - 11-Dec-2026 | Go-Live | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 13 | 4 | 13
TOTAL |  |  |  | 177 | 31 | 32 | 0 | 32 | 0 | 0 | 17.8% | 74 | 30 | 67

## Master Tracker
Master Tracker - all sprints
S.No | Sprint | Module | Task Name | BRD Ref | Layer | Priority | FE Status | BE Status | QA / UAT | STG Deploy | Prod Deploy | Owner | Target Date | Remarks
1 | P5-S1 | RBAC Defaults & Filters | Default permission set - Job object | 4.3 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Gokul
2 | P5-S1 | RBAC Defaults & Filters | Default permission set - Candidate object | 4.3 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Gokul
3 | P5-S1 | RBAC Defaults & Filters | Default permission set - Application object | 4.3 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Gokul
4 | P5-S1 | RBAC Defaults & Filters | Role-driven dynamic search filters | 4.3 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Ehthikash
5 | P5-S1 | RBAC Defaults & Filters | Candidate visibility restriction - recruiter / LOB / location | 4.3 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Ehthikash
6 | P5-S1 | RBAC Defaults & Filters | Recruiter ownership & shared-candidate access | 4.3 | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Ehthikash
7 | P5-S1 | RBAC Defaults & Filters | Elevated visibility for TL / Manager | 4.3 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Ehthikash
8 | P5-S1 | RBAC Defaults & Filters | Override access with approver authorization | 4.3 | Full Stack | Medium | Completed | Completed | Not Started | Deployed | Not Deployed | Ehthikash
9 | P5-S1 | Logging & Timestamp | Central logging framework | 4.21 | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Harish
10 | P5-S1 | Logging & Timestamp | Timestamp logs | 4.21 | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Harish
11 | P5-S1 | Logging & Timestamp | Approval logs | 4.21 | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Harish
12 | P5-S1 | Logging & Timestamp | Workflow transition logs | 4.21 | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Aarthy
13 | P5-S1 | Logging & Timestamp | Activity logs | 4.21 | Backend | Medium | Completed | Completed | Not Started | Deployed | Not Deployed | Harish
14 | P5-S1 | Logging & Timestamp | Centralized log viewer for Admin | 4.21 | Frontend | Medium | Completed | Completed | Not Started | Deployed | Not Deployed | Harish
15 | P5-S1 | Email Notifications | Standard template - Walk-In | 4.9 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Livesh
16 | P5-S1 | Email Notifications | Standard template - On Hold | 4.9 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Livesh
17 | P5-S1 | Email Notifications | Standard template - Rejection | 4.9 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Livesh
18 | P5-S1 | Email Notifications | Standard template - Interview | 4.9 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Livesh
19 | P5-S1 | Email Notifications | Automated trigger engine | 4.9 | Backend | High | Not Applicable | Completed | Not Started | Deployed | Not Deployed | Livesh
20 | P5-S1 | Email Notifications | Personalization tokens & candidate audit mapping | 4.9 | Full Stack | Medium | Completed | Completed | Not Started | Deployed | Not Deployed | Aarthy / Ehthikash
21 | P5-S1 | Email Notifications | Template engine & SMTP configuration | 7 (Dependency) | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Livesh
22 | P5-S1 | Admin Module | Admin user account creation | 4.1 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Gokul
23 | P5-S1 | Admin Module | Admin user list - search, deactivate, reactivate | 4.1 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Gokul
24 | P5-S1 | Admin Module | Granular user-based permission definition | 4.1 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Gokul
25 | P5-S1 | Admin Module | Role-to-permission mapping matrix | 4.1 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Gokul
26 | P5-S1 | Admin Module | Workflow state configuration | 4.1 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Aarthy / Gokul
27 | P5-S1 | Admin Module | Workflow transition configuration | 4.1 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Aarthy / Gokul
28 | P5-S1 | Admin Module | Workflow rule configuration | 4.1 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Aarthy / Gokul
29 | P5-S1 | Admin Module | Workflow versioning | 4.1 | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Aarthy / Gokul
30 | P5-S1 | Admin Module | Workflow change logging | 4.1 | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Aarthy / Gokul
31 | P5-S1 | Admin Module | Invalid workflow state validation | 4.1 | Full Stack | Medium | Completed | Completed | Not Started | Deployed | Not Deployed | Aarthy / Gokul
32 | P5-S1 | Admin Module | Restrict enterprise configuration to Admin | 4.1 | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Gokul
33 | P5-S2 | Admin Module | Secure credential / secret store | 4.1 | Backend | High | In Progress | In Progress | Not Started | Not Deployed | Not Deployed | Gokul / Aarthy
34 | P5-S2 | Admin Module | Secret access control & UI masking | 4.1 | Full Stack | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Gokul
35 | P5-S2 | Admin Module | Secret access logging | 4.1 | Backend | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Gokul / Aarthy
36 | P5-S2 | Admin Module | Encryption at rest and in transit | NFR2 | Backend | High | Not Applicable | In Progress | Not Started | Not Deployed | Not Deployed | Gokul / Aarthy
37 | P5-S2 | Admin Module | Role creation & permission assignment | 4.1 | Full Stack | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Gokul
38 | P5-S2 | Admin Module | Organizational approval hierarchy setup | 4.1 | Full Stack | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Gokul
39 | P5-S2 | Admin Module | Multi-level approver configuration | 4.1 | Full Stack | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Gokul / Aarthy
40 | P5-S2 | Admin Module | Enterprise-level configuration screen | 4.1 | Full Stack | Medium | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Gokul / Aarthy
41 | P5-S2 | Admin Module | Admin module role-based test matrix | 4.1 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed | Gokul
42 | P5-S2 | Assessment Integration | Common assessment integration framework | 4.8 | Backend | High | In Progress | In Progress | Not Started | Not Deployed | Not Deployed | Ehthikash
43 | P5-S2 | Assessment Integration | Versant assessment invocation in workflow | 4.8 | Full Stack | High | In Progress | In Progress | Not Started | Not Deployed | Not Deployed | Ehthikash
44 | P5-S2 | Assessment Integration | Typing & other assessment integration | 4.8 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed | Harish / Aarthy |  | What are the list of integrations needed.. Any preference.
45 | P5-S2 | Assessment Integration | Auto-trigger assessment links by LOB / role | 4.8 | Backend | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Harish
46 | P5-S2 | Assessment Integration | Capture results, timestamps & score validity | 4.8 | Backend | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Harish
47 | P5-S2 | Assessment Integration | 60-day score validity rule engine | 4.7 / 4.8 | Backend | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Livesh
48 | P5-S2 | Assessment Integration | Reschedule flow for technical issues | 4.8 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed | Ehthikash
49 | P5-S2 | Assessment Integration | Approver authorization for technical reschedule | 4.8 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed | Ehthikash
50 | P5-S2 | Assessment Integration | Cooling period rules - SHL assessments | 4.8 | Backend | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Livesh
51 | P5-S2 | Assessment Integration | Voice Fresher Chennai restriction | 4.8 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed | Harish / Aarthy
52 | P5-S2 | Assessment Integration | Assessment audit logging | 4.21 | Backend | Medium | Not Applicable | In Progress | Not Started | Not Deployed | Not Deployed | Harish
53 | P5-S2 | Blacklist Candidate | Blacklist flag with reason capture | Phase 5 backlog | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed | Livesh
54 | P5-S2 | Blacklist Candidate | Block blacklisted candidate from registration / mapping | Phase 5 backlog | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed | Livesh
55 | P5-S2 | Blacklist Candidate | Blacklist audit trail & un-blacklist approval | Phase 5 backlog | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed | Livesh
56 | P5-S3 | Profile Details Modification | Online registration form - mandatory & optional fields | 4.4 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
57 | P5-S3 | Profile Details Modification | Data validation for identity & contact fields | 4.4 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
58 | P5-S3 | Profile Details Modification | Stage-based profile update validation | 4.4 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
59 | P5-S3 | Profile Details Modification | Field lock after applicant creation | 4.4 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
60 | P5-S3 | Profile Details Modification | Candidate profile export to secure PDF | 4.4 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
61 | P5-S3 | Profile Details Modification | Registration completion gate | 4.4 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
62 | P5-S3 | Applicant Changes | Job re-mapping - 6 scenarios | 4.6 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
63 | P5-S3 | Applicant Changes | Walk-In interview scheduling | 4.6 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
64 | P5-S3 | Applicant Changes | Online interview scheduling | 4.6 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
65 | P5-S3 | Applicant Changes | Reject applicant with template & remarks | 4.6 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
66 | P5-S3 | Applicant Changes | Move applicant to HR Interview tab | 4.6 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
67 | P5-S3 | Applicant Changes | Restrict actions to tagged recruiter & TL | 4.6 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
68 | P5-S3 | Applicant Changes | Workflow-driven tab movement validation | 4.6 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
69 | P5-S3 | Applicant Changes | Mandatory logging on scheduling / status change | 4.6 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
70 | P5-S3 | Versant Module | Versant workflow with automated triggers | 4.11 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
71 | P5-S3 | Versant Module | Versant exception handling | 4.11 | Backend | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
72 | P5-S3 | Versant Module | Versant reschedule approval | 4.11 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
73 | P5-S3 | Versant Module | Versant cooling period rules | 4.11 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
74 | P5-S3 | Versant Module | Voice Fresher restriction enforcement | 4.11 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
75 | P5-S3 | Map Candidate | Source management - ERS, Direct, Vendor, Recruiter, Campus, Social | 4.5 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
76 | P5-S3 | Map Candidate | Candidate status identification | 4.5 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
77 | P5-S3 | Map Candidate | Mapping scenarios 1-3 | 4.5 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
78 | P5-S3 | Map Candidate | Mapping scenarios 4-6 | 4.5 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
79 | P5-S3 | Map Candidate | Tag & Map when recruiter not tagged | 4.5 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
80 | P5-S3 | Map Candidate | On Hold routing when positions unavailable | 4.5 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
81 | P5-S3 | Map Candidate | Rejection with standard reason & auto email | 4.5 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
82 | P5-S3 | Map Candidate | Timestamp & remarks capture on mapping actions | 4.5 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
83 | P5-S3 | Map Candidate | Walk-In email trigger | 4.5 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
84 | P5-S3 | Map Candidate | Online interview scheduling from Map Candidate | 4.5 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
85 | P5-S3 | Map Candidate | Pipeline movement from Map Candidate | 4.5 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
86 | P5-S3 | Map Candidate | Active requisition validation on mapping | 4.2 / 4.5 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
87 | P5-S4 | ID Proof Verification | ID proof upload with secure storage | 4.14 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
88 | P5-S4 | ID Proof Verification | External Identity Verification API integration | 4.14 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
89 | P5-S4 | ID Proof Verification | Validation badge for verified candidates | 4.14 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
90 | P5-S4 | ID Proof Verification | Role-restricted access to ID documents | 4.14 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
91 | P5-S4 | ID Proof Verification | Encryption at rest and in transit for ID documents | 4.14 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
92 | P5-S4 | Candidate ID & Photo Validation | Manual photo verification screen for panelists | 4.15 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
93 | P5-S4 | Candidate ID & Photo Validation | Panelist confirm / reject candidate identity | 4.15 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
94 | P5-S4 | Candidate ID & Photo Validation | Auto-highlight photo mismatch rejections | 4.15 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
95 | P5-S4 | Offer Oracle Integration | Candidate to Oracle Offer Interface field mapping | 4.17 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
96 | P5-S4 | Offer Oracle Integration | Offer push API integration | 4.17 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
97 | P5-S4 | Offer Oracle Integration | Pre-push offer validation | 4.17 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
98 | P5-S4 | Offer Oracle Integration | Oracle status change to DigiHire status update | 4.17 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
99 | P5-S4 | Offer Oracle Integration | Offer result synchronization & reconciliation | 4.17 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
100 | P5-S4 | Offer Oracle Integration | Rejected offer auto-revert | 4.17 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
101 | P5-S4 | Offer Oracle Integration | Offer integration error handling & retry log | 4.17 | Backend | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
102 | P5-S4 | Pipeline Enhancements / Bulk Update | Bulk status update across pipeline stages | 4.7 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
103 | P5-S4 | Pipeline Enhancements / Bulk Update | Re-processing based on prior interview stage | 4.7 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
104 | P5-S4 | Pipeline Enhancements / Bulk Update | Re-evaluation on expired score validity | 4.7 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
105 | P5-S4 | Pipeline Enhancements / Bulk Update | Expired score auto-move to Fresher Pipeline | 4.7 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
106 | P5-S4 | Pipeline Enhancements / Bulk Update | Bulk movement via multi-select | 4.7 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
107 | P5-S4 | Pipeline Enhancements / Bulk Update | Bulk movement via Excel upload | 4.7 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
108 | P5-S4 | Pipeline Enhancements / Bulk Update | Stage-history validation on hiring stage movement | 4.7 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
109 | P5-S4 | Jobs Listing Enhancements | Recruiter view of open job requisitions | 4.18 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
110 | P5-S4 | Jobs Listing Enhancements | Job listing search, filter & pagination | 4.18 | Frontend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
111 | P5-S4 | Jobs Listing Enhancements | Publish job to Career Page | 4.18 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
112 | P5-S4 | Jobs Listing Enhancements | Publish job to Buddy Finder | 4.18 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
113 | P5-S4 | Jobs Listing Enhancements | JD edit with TA Head approval | 4.18 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
114 | P5-S4 | Job Integration / LOB Modification | Oracle job requisition sync - create & update | 4.2 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
115 | P5-S4 | Job Integration / LOB Modification | LOB detail sync & modification handling | 4.2 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
116 | P5-S4 | Job Integration / LOB Modification | Incremental change sync | 4.2 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
117 | P5-S4 | Job Integration / LOB Modification | Real-time Job Listing auto-update | 4.2 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
118 | P5-S4 | Job Integration / LOB Modification | Hide invalid / expired jobs from mapping | 4.2 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
119 | P5-S4 | Job Integration / LOB Modification | Oracle to DigiHire field mapping consistency | 4.2 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
120 | P5-S4 | Job Integration / LOB Modification | Job sync failure logging & retry | 4.2 | Backend | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
121 | P5-S5 | HR Round (Online/Offline) | Online interview mode | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
122 | P5-S5 | HR Round (Online/Offline) | In-Office interview mode | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
123 | P5-S5 | HR Round (Online/Offline) | Interview screenshot capture - Online | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
124 | P5-S5 | HR Round (Online/Offline) | Kiosk photo matching - In-Office | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
125 | P5-S5 | HR Round (Online/Offline) | Competency-based feedback configuration | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
126 | P5-S5 | HR Round (Online/Offline) | Feedback entry & scoring | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
127 | P5-S5 | HR Round (Online/Offline) | Movement to Panel based on feedback | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
128 | P5-S5 | HR Round (Online/Offline) | Movement to Assessment based on feedback | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
129 | P5-S5 | HR Round (Online/Offline) | Rejected candidate immediate move to Rejected tab | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
130 | P5-S5 | HR Round (Online/Offline) | Valid next-stage enforcement | 4.10 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
131 | P5-S5 | Panel Interview Enhancements | Panel schedule creation - LOB, panelist, location, ORC ID | 4.12 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
132 | P5-S5 | Panel Interview Enhancements | Recording upload | 4.12 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
133 | P5-S5 | Panel Interview Enhancements | Recording review by authorized roles | 4.12 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
134 | P5-S5 | Panel Interview Enhancements | Panel Select / Reject / Hold handling | 4.12 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
135 | P5-S5 | Panel Interview Enhancements | ORC ID change - same panel path | 4.12 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
136 | P5-S5 | Panel Interview Enhancements | ORC ID change - different panel path | 4.12 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
137 | P5-S5 | Panel Interview Enhancements | 60-day same-ORC reapply restriction | 4.12 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
138 | P5-S5 | Panel Interview Enhancements | Panel reschedule with full remarks history | 4.12 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
139 | P5-S5 | Vendor Module | Vendor onboarding & registration | 4.19 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
140 | P5-S5 | Vendor Module | Vendor document upload | 4.19 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
141 | P5-S5 | Vendor Module | Vendor approval workflow | 4.19 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
142 | P5-S5 | Vendor Module | End-to-end approval logging | 4.19 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
143 | P5-S5 | Vendor Module | Vendor performance dashboard | 4.19 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
144 | P5-S5 | Vendor Module | Vendor task allocation | 4.19 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
145 | P5-S5 | Vendor Module | Target-based allocation restrictions | 4.19 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
146 | P5-S5 | Vendor Module | Vendor task limit enforcement | 4.19 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
147 | P5-S5 | Vendor Module | Auto-archive unregistered vendor profiles | 4.19 | Backend | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
148 | P5-S5 | Vendor Module | Vendor-sourced candidate linkage | 4.19 / 4.5 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
149 | P5-S5 | Vendor Module | Vendor role & permission mapping | 4.19 / 4.3 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
150 | P5-S5 | Vendor Module | Three end-to-end vendor scenarios | 8 (Acceptance) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
151 | P5-S6 | Dashboard & Reporting | Dashboard search & filter enhancements | 4.20 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
152 | P5-S6 | Dashboard & Reporting | Drill-down from dashboard widgets | 4.20 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
153 | P5-S6 | Dashboard & Reporting | Hiring funnel report | 4.20 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
154 | P5-S6 | Dashboard & Reporting | Vendor performance report | 4.20 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
155 | P5-S6 | Dashboard & Reporting | Recruiter performance report | 4.20 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
156 | P5-S6 | Dashboard & Reporting | Report export - Excel / PDF | 4.20 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
157 | P5-S6 | Dashboard & Reporting | Role-based dashboard & report access | 4.20 / 4.3 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
158 | P5-S6 | Dashboard & Reporting | TL and above requisition upload / modify | 4.20 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
159 | P5-S6 | Dashboard & Reporting | Report accuracy validation >=99% | 8 (Acceptance) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
160 | P5-S6 | Optimization & Tuning | Map Candidate page optimization | 4.23 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
161 | P5-S6 | Optimization & Tuning | Applicant page optimization | 4.23 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
162 | P5-S6 | Optimization & Tuning | Dashboard load time reduction | 4.23 / NFR1 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
163 | P5-S6 | Optimization & Tuning | Database indexing & query tuning | 4.23 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
164 | P5-S6 | Optimization & Tuning | Concurrency handling improvements | 4.23 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
165 | P5-S6 | Optimization & Tuning | Scalability validation to 5x volume | NFR3 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
166 | P5-S6 | Build Stabilization | Defect triage & Sev1 / Sev2 closure | 8 (Acceptance) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
167 | P5-S6 | Build Stabilization | Known defect fixes across existing flows | 4.23 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
168 | P5-S6 | Build Stabilization | End-to-end regression - sourcing to onboarding | 8 (Acceptance) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
169 | P5-S6 | Build Stabilization | Integration regression - Oracle, SHL, Versant, ID Verification | 8 (Acceptance) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
170 | P5-S6 | Build Stabilization | RBAC & permission regression matrix | 4.3 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
171 | P5-S6 | Build Stabilization | Rule verification - cooling period, ORC, Voice Fresher | 8 (Acceptance) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
172 | P5-S6 | Build Stabilization | Audit log completeness verification | NFR5 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
173 | P5-S6 | Build Stabilization | Performance re-test - 3s load, 99.5% uptime | NFR1 / NFR4 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
174 | P5-S6 | Build Stabilization | UAT support & defect turnaround | 1 (Intro) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
175 | P5-S6 | Build Stabilization | User training material & documentation | 9 (Deliverables) | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
176 | P5-S6 | Build Stabilization | Go-Live readiness checklist & cutover plan | 9 (Deliverables) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
177 | P5-S6 | Build Stabilization | Production deployment & hypercare | 9 (Deliverables) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed

## P5-S1
P5-S1 ¦ Weeks 11-12 ¦ 21-Sep - 02-Oct-2026
S.No | Module | Task Name | BRD Ref | Layer | Priority | FE Status | BE Status | QA / UAT | STG Deploy | Prod Deploy | Owner | Target Date | Remarks
1 | RBAC Defaults & Filters | Default permission set - Job object | 4.3 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Gokul
2 | RBAC Defaults & Filters | Default permission set - Candidate object | 4.3 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Gokul
3 | RBAC Defaults & Filters | Default permission set - Application object | 4.3 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Gokul
4 | RBAC Defaults & Filters | Role-driven dynamic search filters | 4.3 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Ehthikash
5 | RBAC Defaults & Filters | Candidate visibility restriction - recruiter / LOB / location | 4.3 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Ehthikash
6 | RBAC Defaults & Filters | Recruiter ownership & shared-candidate access | 4.3 | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Ehthikash
7 | RBAC Defaults & Filters | Elevated visibility for TL / Manager | 4.3 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Ehthikash
8 | RBAC Defaults & Filters | Override access with approver authorization | 4.3 | Full Stack | Medium | Completed | Completed | Not Started | Deployed | Not Deployed | Ehthikash
9 | Logging & Timestamp | Central logging framework | 4.21 | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Harish
10 | Logging & Timestamp | Timestamp logs | 4.21 | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Harish
11 | Logging & Timestamp | Approval logs | 4.21 | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Harish
12 | Logging & Timestamp | Workflow transition logs | 4.21 | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Aarthy
13 | Logging & Timestamp | Activity logs | 4.21 | Backend | Medium | Completed | Completed | Not Started | Deployed | Not Deployed | Harish
14 | Logging & Timestamp | Centralized log viewer for Admin | 4.21 | Frontend | Medium | Completed | Completed | Not Started | Deployed | Not Deployed | Harish
15 | Email Notifications | Standard template - Walk-In | 4.9 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Livesh
16 | Email Notifications | Standard template - On Hold | 4.9 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Livesh
17 | Email Notifications | Standard template - Rejection | 4.9 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Livesh
18 | Email Notifications | Standard template - Interview | 4.9 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Livesh
19 | Email Notifications | Automated trigger engine | 4.9 | Backend | High | Not Applicable | Completed | Not Started | Deployed | Not Deployed | Livesh
20 | Email Notifications | Personalization tokens & candidate audit mapping | 4.9 | Full Stack | Medium | Completed | Completed | Not Started | Deployed | Not Deployed | Aarthy / Ehthikash
21 | Email Notifications | Template engine & SMTP configuration | 7 (Dependency) | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Livesh
22 | Admin Module | Admin user account creation | 4.1 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Gokul
23 | Admin Module | Admin user list - search, deactivate, reactivate | 4.1 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Gokul
24 | Admin Module | Granular user-based permission definition | 4.1 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Gokul
25 | Admin Module | Role-to-permission mapping matrix | 4.1 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Gokul
26 | Admin Module | Workflow state configuration | 4.1 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Aarthy / Gokul
27 | Admin Module | Workflow transition configuration | 4.1 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Aarthy / Gokul
28 | Admin Module | Workflow rule configuration | 4.1 | Full Stack | High | Completed | Completed | Not Started | Deployed | Not Deployed | Aarthy / Gokul
29 | Admin Module | Workflow versioning | 4.1 | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Aarthy / Gokul
30 | Admin Module | Workflow change logging | 4.1 | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Aarthy / Gokul
31 | Admin Module | Invalid workflow state validation | 4.1 | Full Stack | Medium | Completed | Completed | Not Started | Deployed | Not Deployed | Aarthy / Gokul
32 | Admin Module | Restrict enterprise configuration to Admin | 4.1 | Backend | High | Completed | Completed | Not Started | Deployed | Not Deployed | Gokul

## P5-S2
P5-S2 ¦ Weeks 13-14 ¦ 05-Oct - 16-Oct-2026
S.No | Module | Task Name | BRD Ref | Layer | Priority | FE Status | BE Status | QA / UAT | STG Deploy | Prod Deploy | Owner | Target Date | Remarks
1 | Admin Module | Secure credential / secret store | 4.1 | Backend | High | In Progress | In Progress | Not Started | Not Deployed | Not Deployed | Gokul / Aarthy
2 | Admin Module | Secret access control & UI masking | 4.1 | Full Stack | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Gokul
3 | Admin Module | Secret access logging | 4.1 | Backend | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Gokul / Aarthy
4 | Admin Module | Encryption at rest and in transit | NFR2 | Backend | High | Not Applicable | In Progress | Not Started | Not Deployed | Not Deployed | Gokul / Aarthy
5 | Admin Module | Role creation & permission assignment | 4.1 | Full Stack | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Gokul
6 | Admin Module | Organizational approval hierarchy setup | 4.1 | Full Stack | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Gokul
7 | Admin Module | Multi-level approver configuration | 4.1 | Full Stack | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Gokul / Aarthy
8 | Admin Module | Enterprise-level configuration screen | 4.1 | Full Stack | Medium | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Gokul / Aarthy
9 | Admin Module | Admin module role-based test matrix | 4.1 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed | Gokul
10 | Assessment Integration | Common assessment integration framework | 4.8 | Backend | High | In Progress | In Progress | Not Started | Not Deployed | Not Deployed | Ehthikash
11 | Assessment Integration | Versant assessment invocation in workflow | 4.8 | Full Stack | High | In Progress | In Progress | Not Started | Not Deployed | Not Deployed | Ehthikash
12 | Assessment Integration | Typing assessment integration | 4.8 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed | Harish / Aarthy |  | What are the list of integrations needed.. Any preference.
13 | Assessment Integration | Auto-trigger assessment links by LOB / role | 4.8 | Backend | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Harish
14 | Assessment Integration | Capture results, timestamps & score validity | 4.8 | Backend | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Harish
15 | Assessment Integration | 60-day score validity rule engine | 4.7 / 4.8 | Backend | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Livesh
16 | Assessment Integration | Reschedule flow for technical issues | 4.8 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed | Ehthikash
17 | Assessment Integration | Approver authorization for technical reschedule | 4.8 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed | Ehthikash
18 | Assessment Integration | Cooling period rules - SHL assessments | 4.8 | Backend | High | Not Started | In Progress | Not Started | Not Deployed | Not Deployed | Livesh
19 | Assessment Integration | Voice Fresher Chennai restriction | 4.8 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed | Harish / Aarthy
20 | Assessment Integration | Assessment audit logging | 4.21 | Backend | Medium | Not Applicable | In Progress | Not Started | Not Deployed | Not Deployed | Harish
21 | Blacklist Candidate | Blacklist flag with reason capture | Phase 5 backlog | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed | Livesh
22 | Blacklist Candidate | Block blacklisted candidate from registration / mapping | Phase 5 backlog | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed | Livesh
23 | Blacklist Candidate | Blacklist audit trail & un-blacklist approval | Phase 5 backlog | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed | Livesh

## P5-S3
P5-S3 ¦ Weeks 15-16 ¦ 19-Oct - 30-Oct-2026
S.No | Module | Task Name | BRD Ref | Layer | Priority | FE Status | BE Status | QA / UAT | STG Deploy | Prod Deploy | Owner | Target Date | Remarks
1 | Profile Details Modification | Online registration form - mandatory & optional fields | 4.4 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
2 | Profile Details Modification | Data validation for identity & contact fields | 4.4 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
3 | Profile Details Modification | Stage-based profile update validation | 4.4 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
4 | Profile Details Modification | Field lock after applicant creation | 4.4 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
5 | Profile Details Modification | Candidate profile export to secure PDF | 4.4 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
6 | Profile Details Modification | Registration completion gate | 4.4 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
7 | Applicant Changes | Job re-mapping - 6 scenarios | 4.6 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
8 | Applicant Changes | Walk-In interview scheduling | 4.6 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
9 | Applicant Changes | Online interview scheduling | 4.6 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
10 | Applicant Changes | Reject applicant with template & remarks | 4.6 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
11 | Applicant Changes | Move applicant to HR Interview tab | 4.6 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
12 | Applicant Changes | Restrict actions to tagged recruiter & TL | 4.6 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
13 | Applicant Changes | Workflow-driven tab movement validation | 4.6 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
14 | Applicant Changes | Mandatory logging on scheduling / status change | 4.6 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
15 | Versant Module | Versant workflow with automated triggers | 4.11 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
16 | Versant Module | Versant exception handling | 4.11 | Backend | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
17 | Versant Module | Versant reschedule approval | 4.11 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
18 | Versant Module | Versant cooling period rules | 4.11 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
19 | Versant Module | Voice Fresher restriction enforcement | 4.11 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
20 | Map Candidate | Source management - ERS, Direct, Vendor, Recruiter, Campus, Social | 4.5 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
21 | Map Candidate | Candidate status identification | 4.5 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
22 | Map Candidate | Mapping scenarios 1-3 | 4.5 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
23 | Map Candidate | Mapping scenarios 4-6 | 4.5 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
24 | Map Candidate | Tag & Map when recruiter not tagged | 4.5 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
25 | Map Candidate | On Hold routing when positions unavailable | 4.5 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
26 | Map Candidate | Rejection with standard reason & auto email | 4.5 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
27 | Map Candidate | Timestamp & remarks capture on mapping actions | 4.5 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
28 | Map Candidate | Walk-In email trigger | 4.5 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
29 | Map Candidate | Online interview scheduling from Map Candidate | 4.5 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
30 | Map Candidate | Pipeline movement from Map Candidate | 4.5 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
31 | Map Candidate | Active requisition validation on mapping | 4.2 / 4.5 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed

## P5-S4
P5-S4 ¦ Weeks 17-18 ¦ 02-Nov - 13-Nov-2026
S.No | Module | Task Name | BRD Ref | Layer | Priority | FE Status | BE Status | QA / UAT | STG Deploy | Prod Deploy | Owner | Target Date | Remarks
1 | ID Proof Verification | ID proof upload with secure storage | 4.14 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
2 | ID Proof Verification | External Identity Verification API integration | 4.14 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
3 | ID Proof Verification | Validation badge for verified candidates | 4.14 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
4 | ID Proof Verification | Role-restricted access to ID documents | 4.14 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
5 | ID Proof Verification | Encryption at rest and in transit for ID documents | 4.14 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
6 | Candidate ID & Photo Validation | Manual photo verification screen for panelists | 4.15 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
7 | Candidate ID & Photo Validation | Panelist confirm / reject candidate identity | 4.15 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
8 | Candidate ID & Photo Validation | Auto-highlight photo mismatch rejections | 4.15 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
9 | Offer Oracle Integration | Candidate to Oracle Offer Interface field mapping | 4.17 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
10 | Offer Oracle Integration | Offer push API integration | 4.17 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
11 | Offer Oracle Integration | Pre-push offer validation | 4.17 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
12 | Offer Oracle Integration | Oracle status change to DigiHire status update | 4.17 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
13 | Offer Oracle Integration | Offer result synchronization & reconciliation | 4.17 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
14 | Offer Oracle Integration | Rejected offer auto-revert | 4.17 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
15 | Offer Oracle Integration | Offer integration error handling & retry log | 4.17 | Backend | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
16 | Pipeline Enhancements / Bulk Update | Bulk status update across pipeline stages | 4.7 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
17 | Pipeline Enhancements / Bulk Update | Re-processing based on prior interview stage | 4.7 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
18 | Pipeline Enhancements / Bulk Update | Re-evaluation on expired score validity | 4.7 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
19 | Pipeline Enhancements / Bulk Update | Expired score auto-move to Fresher Pipeline | 4.7 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
20 | Pipeline Enhancements / Bulk Update | Bulk movement via multi-select | 4.7 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
21 | Pipeline Enhancements / Bulk Update | Bulk movement via Excel upload | 4.7 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
22 | Pipeline Enhancements / Bulk Update | Stage-history validation on hiring stage movement | 4.7 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
23 | Jobs Listing Enhancements | Recruiter view of open job requisitions | 4.18 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
24 | Jobs Listing Enhancements | Job listing search, filter & pagination | 4.18 | Frontend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
25 | Jobs Listing Enhancements | Publish job to Career Page | 4.18 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
26 | Jobs Listing Enhancements | Publish job to Buddy Finder | 4.18 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
27 | Jobs Listing Enhancements | JD edit with TA Head approval | 4.18 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
28 | Job Integration / LOB Modification | Oracle job requisition sync - create & update | 4.2 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
29 | Job Integration / LOB Modification | LOB detail sync & modification handling | 4.2 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
30 | Job Integration / LOB Modification | Incremental change sync | 4.2 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
31 | Job Integration / LOB Modification | Real-time Job Listing auto-update | 4.2 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
32 | Job Integration / LOB Modification | Hide invalid / expired jobs from mapping | 4.2 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
33 | Job Integration / LOB Modification | Oracle to DigiHire field mapping consistency | 4.2 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
34 | Job Integration / LOB Modification | Job sync failure logging & retry | 4.2 | Backend | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed

## P5-S5
P5-S5 ¦ Weeks 19-20 ¦ 16-Nov - 27-Nov-2026
S.No | Module | Task Name | BRD Ref | Layer | Priority | FE Status | BE Status | QA / UAT | STG Deploy | Prod Deploy | Owner | Target Date | Remarks
1 | HR Round (Online/Offline) | Online interview mode | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
2 | HR Round (Online/Offline) | In-Office interview mode | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
3 | HR Round (Online/Offline) | Interview screenshot capture - Online | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
4 | HR Round (Online/Offline) | Kiosk photo matching - In-Office | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
5 | HR Round (Online/Offline) | Competency-based feedback configuration | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
6 | HR Round (Online/Offline) | Feedback entry & scoring | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
7 | HR Round (Online/Offline) | Movement to Panel based on feedback | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
8 | HR Round (Online/Offline) | Movement to Assessment based on feedback | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
9 | HR Round (Online/Offline) | Rejected candidate immediate move to Rejected tab | 4.10 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
10 | HR Round (Online/Offline) | Valid next-stage enforcement | 4.10 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
11 | Panel Interview Enhancements | Panel schedule creation - LOB, panelist, location, ORC ID | 4.12 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
12 | Panel Interview Enhancements | Recording upload | 4.12 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
13 | Panel Interview Enhancements | Recording review by authorized roles | 4.12 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
14 | Panel Interview Enhancements | Panel Select / Reject / Hold handling | 4.12 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
15 | Panel Interview Enhancements | ORC ID change - same panel path | 4.12 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
16 | Panel Interview Enhancements | ORC ID change - different panel path | 4.12 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
17 | Panel Interview Enhancements | 60-day same-ORC reapply restriction | 4.12 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
18 | Panel Interview Enhancements | Panel reschedule with full remarks history | 4.12 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
19 | Vendor Module | Vendor onboarding & registration | 4.19 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
20 | Vendor Module | Vendor document upload | 4.19 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
21 | Vendor Module | Vendor approval workflow | 4.19 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
22 | Vendor Module | End-to-end approval logging | 4.19 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
23 | Vendor Module | Vendor performance dashboard | 4.19 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
24 | Vendor Module | Vendor task allocation | 4.19 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
25 | Vendor Module | Target-based allocation restrictions | 4.19 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
26 | Vendor Module | Vendor task limit enforcement | 4.19 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
27 | Vendor Module | Auto-archive unregistered vendor profiles | 4.19 | Backend | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
28 | Vendor Module | Vendor-sourced candidate linkage | 4.19 / 4.5 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
29 | Vendor Module | Vendor role & permission mapping | 4.19 / 4.3 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
30 | Vendor Module | Three end-to-end vendor scenarios | 8 (Acceptance) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed

## P5-S6
P5-S6 ¦ Weeks 21-22 ¦ 30-Nov - 11-Dec-2026
S.No | Module | Task Name | BRD Ref | Layer | Priority | FE Status | BE Status | QA / UAT | STG Deploy | Prod Deploy | Owner | Target Date | Remarks
1 | Dashboard & Reporting | Dashboard search & filter enhancements | 4.20 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
2 | Dashboard & Reporting | Drill-down from dashboard widgets | 4.20 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
3 | Dashboard & Reporting | Hiring funnel report | 4.20 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
4 | Dashboard & Reporting | Vendor performance report | 4.20 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
5 | Dashboard & Reporting | Recruiter performance report | 4.20 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
6 | Dashboard & Reporting | Report export - Excel / PDF | 4.20 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
7 | Dashboard & Reporting | Role-based dashboard & report access | 4.20 / 4.3 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
8 | Dashboard & Reporting | TL and above requisition upload / modify | 4.20 | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
9 | Dashboard & Reporting | Report accuracy validation >=99% | 8 (Acceptance) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
10 | Optimization & Tuning | Map Candidate page optimization | 4.23 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
11 | Optimization & Tuning | Applicant page optimization | 4.23 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
12 | Optimization & Tuning | Dashboard load time reduction | 4.23 / NFR1 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
13 | Optimization & Tuning | Database indexing & query tuning | 4.23 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
14 | Optimization & Tuning | Concurrency handling improvements | 4.23 | Backend | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
15 | Optimization & Tuning | Scalability validation to 5x volume | NFR3 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
16 | Build Stabilization | Defect triage & Sev1 / Sev2 closure | 8 (Acceptance) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
17 | Build Stabilization | Known defect fixes across existing flows | 4.23 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
18 | Build Stabilization | End-to-end regression - sourcing to onboarding | 8 (Acceptance) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
19 | Build Stabilization | Integration regression - Oracle, SHL, Versant, ID Verification | 8 (Acceptance) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
20 | Build Stabilization | RBAC & permission regression matrix | 4.3 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
21 | Build Stabilization | Rule verification - cooling period, ORC, Voice Fresher | 8 (Acceptance) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
22 | Build Stabilization | Audit log completeness verification | NFR5 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
23 | Build Stabilization | Performance re-test - 3s load, 99.5% uptime | NFR1 / NFR4 | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
24 | Build Stabilization | UAT support & defect turnaround | 1 (Intro) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
25 | Build Stabilization | User training material & documentation | 9 (Deliverables) | Full Stack | Medium | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
26 | Build Stabilization | Go-Live readiness checklist & cutover plan | 9 (Deliverables) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed
27 | Build Stabilization | Production deployment & hypercare | 9 (Deliverables) | Full Stack | High | Not Started | Not Started | Not Started | Not Deployed | Not Deployed

## Dependencies
Sprint Dependency Register
Dep ID | Sprint | Dependency | Category | Type | Owner | Team | Required By | Status | Remarks
DEP-S1-01 | P5-S1 | SMTP server & email template engine configuration | Email Template | External | TA Head | TA Head / Leadership | Before 21-Sep | Not Started | Need confirmation whether we will be using the same set as before. Template will be handled in the code.
DEP-S1-02 | P5-S1 | Email domain whitelisting (SPF / DKIM / DMARC) for candidate mails | Infrastructure | External | AGS IT / Security | AGS Security, Legal & Compliance | Before 21-Sep | Closed
DEP-S1-03 | P5-S1 | Role, LOB and Location master data | Data / Configuration | Internal | AGS TA Ops | AGS TA Ops / BA | Before 21-Sep | Not Started
DEP-S1-04 | P5-S1 | Signed-off RBAC permission matrix (role x object x action) | Approval / Sign-off | Internal | TA Head / Suresh | TA Head / Leadership | Before 21-Sep | Not Started
DEP-S1-05 | P5-S1 | Log table schema, storage sizing & retention policy | AGS Software | Internal | AGS Tech | AGS IT & Infra | Before 21-Sep | Not Started | Paddy can give these details.
DEP-S1-06 | P5-S1 | STG environments provisioned for Phase 5 | Environment | Internal | AGS IT / DevOps | AGS IT & Infra | Before 21-Sep | Closed
DEP-S1-07 | P5-S1 | Confirmation that Phase 5 = 120 days IN-SCOPE (RBAC in, 4 items out) | Approval / Sign-off | Internal | Suresh Divakaran | TA Head / Leadership | Before 21-Sep | Closed
DEP-S1-08 | P5-S1 | Central logging framework delivered in week 1 of P5-S1 | Predecessor Work | Internal | Dev Team | Dev Team (Internal) | By 25-Sep | In Progress
DEP-S1-09 | P5-S1 | RBAC permission framework delivered in week 1 of P5-S1 | Predecessor Work | Internal | Dev Team | Dev Team (Internal) | By 25-Sep | In Progress
DEP-S1-10 | P5-S1 | Workflow state and transition catalogue per module | Data / Configuration | Internal | TA Head | AGS TA Ops / BA | Before 21-Sep | Not Started | Matrix for the LOB and Assessments to map the list of assessments for each type of Role under LOB
DEP-S1-11 | P5-S1 | Admin role definitions and hierarchy inputs | Approval / Sign-off | Internal | TA Head | TA Head / Leadership | Before 21-Sep | Not Started
DEP-S1-12 | P5-S1 | Admin test accounts and sample user data on STG | Environment | Internal | AGS IT | AGS IT & Infra | Before 21-Sep | Not Started
DEP-S2-01 | P5-S2 | Blacklist reason master list | Data / Configuration | Internal | AGS TA Ops | AGS TA Ops / BA | Before 05-Oct | Not Started
DEP-S2-02 | P5-S2 | Vendor credentials issued - Versant, Oracle, ID Verification | Vendor / 3rd Party | External | Vendor Partners / AGS Procurement | Vendors & Procurement | Before 05-Oct | Not Started
DEP-S2-03 | P5-S2 | Secrets management / vault solution decision and provisioning | Infrastructure | External | AGS Infra & Security | AGS Security, Legal & Compliance | Before 05-Oct | Not Started | DevOps Work. Owned by AGS Team.
DEP-S2-04 | P5-S2 | Encryption key management (KMS) and key rotation policy | Infrastructure | External | AGS Security | AGS Security, Legal & Compliance | Before 05-Oct | Not Started | DevOps Work. Owned by AGS Team.
DEP-S2-05 | P5-S2 | Organizational approval hierarchy data (approvers by level and LOB) | Data / Configuration | Internal | AGS TA Ops / HR | AGS TA Ops / BA | Before 05-Oct | Not Started
DEP-S2-06 | P5-S2 | Security team review of secret handling design | Approval / Sign-off | External | AGS Security | AGS Security, Legal & Compliance | Before 05-Oct | Not Started | DevOps Work. Owned by AGS Team.
DEP-S2-07 | P5-S2 | Versant API access and sandbox environment | Vendor / 3rd Party | External | Versant | Vendors & Procurement | Before 05-Oct | Closed
DEP-S2-08 | P5-S2 | Typing / other assessment tool API access | Vendor / 3rd Party | External | Assessment Vendor | Vendors & Procurement | Before 05-Oct | Closed | SHL, Versant and Panel Only
DEP-S2-09 | P5-S2 | LOB / role to assessment mapping matrix | Data / Configuration | Internal | AGS TA Ops | AGS TA Ops / BA | Before 05-Oct | Not Started
DEP-S2-10 | P5-S2 | Cooling period rules sign-off (SHL 7/30/180, Versant 15/45/180) | Approval / Sign-off | Internal | TA Head / Suresh | TA Head / Leadership | Before 05-Oct | Not Started
DEP-S2-11 | P5-S2 | Voice Fresher Chennai restriction definition and role list | Data / Configuration | Internal | AGS TA Ops | AGS TA Ops / BA | Before 05-Oct | Not Started
DEP-S2-12 | P5-S2 | Secrets vault delivered in week 1 of P5-S2 | Predecessor Work | Internal | Dev Team | Dev Team (Internal) | By 09-Oct | Not Started | DevOps Work. Owned by AGS Team.
DEP-S3-01 | P5-S3 | Final registration field list - mandatory vs optional | Approval / Sign-off | Internal | TA Head / BA | TA Head / Leadership | Before 19-Oct | Not Started
DEP-S3-02 | P5-S3 | Stage-wise editable field matrix (post applicant creation) | Data / Configuration | Internal | AGS TA Ops / BA | AGS TA Ops / BA | Before 19-Oct | Not Started
DEP-S3-03 | P5-S3 | Secure PDF template and branding for profile export | Data / Configuration | Internal | AGS TA / Marketing | AGS Marketing / Web | Before 19-Oct | Not Started
DEP-S3-04 | P5-S3 | Versant API availability (carried from P5-S2) | Vendor / 3rd Party | External | Versant | Vendors & Procurement | Before 19-Oct | Not Started
DEP-S3-05 | P5-S3 | Email templates delivered in P5-S1 | Predecessor Work | Internal | Dev Team | Dev Team (Internal) | Before 19-Oct | Not Started
DEP-S3-06 | P5-S3 | Six mapping scenario definitions (shared with Map Candidate) | Approval / Sign-off | Internal | BA / TA Ops | AGS TA Ops / BA | Before 19-Oct | Not Started
DEP-S3-07 | P5-S3 | Interview slot / calendar master for Walk-In and Online modes | Data / Configuration | Internal | AGS TA Ops | AGS TA Ops / BA | Before 19-Oct | Not Started
DEP-S3-08 | P5-S3 | Sourcing channel master and ERS data feed | Data / Configuration | Internal | AGS TA Ops / ERS Owner | AGS TA Ops / BA | Before 19-Oct | Not Started
DEP-S3-09 | P5-S3 | Standard rejection reason master list | Data / Configuration | Internal | AGS TA Ops | AGS TA Ops / BA | Before 19-Oct | Not Started
DEP-S3-10 | P5-S3 | Oracle requisition validity feed (active vs expired jobs) | Vendor / 3rd Party | External | Oracle Team | Oracle Team | Before 19-Oct | Not Started
DEP-S4-01 | P5-S4 | External Identity Verification API - contract, credentials, rate limits | Vendor / 3rd Party | External | ID Verification Vendor / Procurement | Vendors & Procurement | Before 02-Nov | Not Started
DEP-S4-02 | P5-S4 | Secure document storage with encryption (object store / DMS) | Infrastructure | External | AGS Infra & Security | AGS IT & Infra | Before 02-Nov | Not Started
DEP-S4-03 | P5-S4 | Data privacy, consent and retention approval for ID documents | Approval / Sign-off | External | AGS Legal / Compliance | AGS Security, Legal & Compliance | Before 02-Nov | Not Started
DEP-S4-04 | P5-S4 | Panelist photo verification process sign-off | Approval / Sign-off | Internal | TA Head / Compliance | TA Head / Leadership | Before 02-Nov | Not Started
DEP-S4-05 | P5-S4 | Oracle Offer Interface - API spec, endpoints, credentials, sandbox | Vendor / 3rd Party | External | Oracle Team / AGS IT | Oracle Team | Before 02-Nov | Not Started
DEP-S4-06 | P5-S4 | Oracle offer field mapping document sign-off | Approval / Sign-off | External | Oracle Team / TA Head | Oracle Team | Before 02-Nov | Not Started
DEP-S4-07 | P5-S4 | Oracle status callback or polling mechanism agreement | Vendor / 3rd Party | External | Oracle Team | Oracle Team | Before 02-Nov | Not Started
DEP-S4-08 | P5-S4 | Test offer records and test candidates in the Oracle sandbox | Environment | External | Oracle Team | Oracle Team | Before 02-Nov | Not Started
DEP-S4-09 | P5-S4 | 60-day score validity engine delivered in P5-S2 | Predecessor Work | Internal | Dev Team | Dev Team (Internal) | Before 02-Nov | Not Started
DEP-S4-10 | P5-S4 | Bulk Excel upload template format sign-off | Approval / Sign-off | Internal | TA Ops / BA | AGS TA Ops / BA | Before 02-Nov | Not Started
DEP-S4-11 | P5-S4 | Oracle job requisition and LOB sync API + incremental change feed | Vendor / 3rd Party | External | Oracle Team | Oracle Team | Before 02-Nov | Not Started
DEP-S4-12 | P5-S4 | Oracle to DigiHire job field mapping sign-off | Approval / Sign-off | External | Oracle Team / BA | Oracle Team | Before 02-Nov | Not Started
DEP-S4-13 | P5-S4 | Career Page publishing endpoint / CMS access | Vendor / 3rd Party | External | AGS Marketing / Web Team | AGS Marketing / Web | Before 02-Nov | Not Started
DEP-S4-14 | P5-S4 | Buddy Finder platform access / API | Vendor / 3rd Party | External | Buddy Finder Owner | Vendors & Procurement | Before 02-Nov | Not Started
DEP-S4-15 | P5-S4 | JD edit approval workflow definition (TA Head approval) | Approval / Sign-off | Internal | TA Head | TA Head / Leadership | Before 02-Nov | Not Started
DEP-S5-01 | P5-S5 | Kiosk photo capture hardware and SDK at interview locations | Vendor / 3rd Party | External | AGS IT / Facilities | AGS IT & Infra | Before 16-Nov | Closed
DEP-S5-02 | P5-S5 | Online interview platform - link generation and screenshot capability | Vendor / 3rd Party | External | AGS IT / Platform Vendor | AGS IT & Infra | Before 16-Nov | Not Started
DEP-S5-03 | P5-S5 | Recording storage capacity and retention policy | Infrastructure | External | AGS Infra / Compliance | AGS IT & Infra | Before 16-Nov | Not Started
DEP-S5-04 | P5-S5 | Competency framework and feedback form definitions | Data / Configuration | Internal | TA Head / HR | TA Head / Leadership | Before 16-Nov | Not Started
DEP-S5-05 | P5-S5 | ORC ID master, panel and panelist master data | Data / Configuration | Internal | AGS TA Ops | AGS TA Ops / BA | Before 16-Nov | Not Started
DEP-S5-06 | P5-S5 | Interview location and panel calendar master | Data / Configuration | Internal | AGS TA Ops | AGS TA Ops / BA | Before 16-Nov | Not Started
DEP-S5-07 | P5-S5 | Vendor master data, contracts and commercial targets | Data / Configuration | Internal | AGS Procurement / TA | Vendors & Procurement | Before 16-Nov | Not Started
DEP-S5-08 | P5-S5 | Vendor document checklist and agreement templates | Approval / Sign-off | External | AGS Legal / Procurement | AGS Security, Legal & Compliance | Before 16-Nov | Not Started
DEP-S5-09 | P5-S5 | Vendor approval hierarchy sign-off | Approval / Sign-off | Internal | TA Head | TA Head / Leadership | Before 16-Nov | Not Started
DEP-S5-10 | P5-S5 | External vendor user access model and email deliverability | Infrastructure | External | AGS IT / Security | AGS Security, Legal & Compliance | Before 16-Nov | Closed
DEP-S5-11 | P5-S5 | Vendor performance KPI definitions | Data / Configuration | Internal | TA Head | TA Head / Leadership | Before 16-Nov | Not Started
DEP-S5-12 | P5-S5 | Three end-to-end vendor test scenarios agreed | Approval / Sign-off | Internal | TA Ops / QA | AGS TA Ops / BA | Before 16-Nov | Not Started
DEP-S6-01 | P5-S6 | Report and KPI specification sign-off (funnel, vendor, recruiter) | Approval / Sign-off | Internal | TA Head | TA Head / Leadership | Before 30-Nov | Not Started
DEP-S6-02 | P5-S6 | Production-like data volume for high-volume and 5x scalability testing | Environment | Internal | AGS DBA / IT | AGS IT & Infra | Before 30-Nov | Not Started
DEP-S6-03 | P5-S6 | Performance testing tool, licences and load environment | Environment | External | AGS IT / DevOps | AGS IT & Infra | Before 30-Nov | Not Started
DEP-S6-04 | P5-S6 | DBA support for indexing and query tuning | Resource | Internal | AGS DBA | AGS IT & Infra | Before 30-Nov | Not Started
DEP-S6-05 | P5-S6 | APM / monitoring tooling access (logs, traces, DB metrics) | Infrastructure | External | AGS IT | AGS IT & Infra | Before 30-Nov | Not Started
DEP-S6-06 | P5-S6 | Infrastructure sizing confirmation for peak load | Approval / Sign-off | External | AGS Infra | AGS IT & Infra | Before 30-Nov | Not Started
DEP-S6-07 | P5-S6 | UAT environment with masked production-like data | Environment | Internal | AGS IT / DBA | AGS IT & Infra | Before 30-Nov | Not Started
DEP-S6-08 | P5-S6 | UAT users nominated and available (TA, HR, Vendors) | Resource | Internal | TA Head | TA Head / Leadership | Before 30-Nov | Not Started
DEP-S6-09 | P5-S6 | Production credentials for all integrations - Oracle, Versant, ID Verification | Vendor / 3rd Party | External | Vendor Partners / AGS IT | Vendors & Procurement | Before 30-Nov | Not Started
DEP-S6-10 | P5-S6 | Change Advisory Board / release approval | Approval / Sign-off | Internal | AGS IT Governance | AGS IT & Infra | Before 30-Nov | Not Started
DEP-S6-11 | P5-S6 | Production deployment window and downtime approval | Approval / Sign-off | Internal | AGS IT / Business | AGS IT & Infra | Before 30-Nov | Not Started
DEP-S6-12 | P5-S6 | Training schedule, trainer and training environment | Resource | Internal | TA Head / L&D | TA Head / Leadership | Before 30-Nov | Not Started
DEP-S6-13 | P5-S6 | Hypercare support roster and escalation matrix | Resource | Internal | PM / Dev Team | Dev Team (Internal) | Before 30-Nov | Not Started

## Oracle
Jobs
Create API
Update API
Get All
Get by Id
Candidates
Create API
Update API
Get by Email
Employees
Get by Email

## Deps by Team
Dependencies by Team and Category
Team | Infrastructure | Environment | Data / Configuration | Approval / Sign-off | Vendor / 3rd Party | Predecessor Work | Resource | Total
AGS IT & Infra | 3 | 5 | 0 | 3 | 2 | 0 | 1 | 14
AGS Security, Legal & Compliance | 4 | 0 | 0 | 3 | 0 | 0 | 0 | 7
AGS TA Ops / BA | 0 | 0 | 12 | 3 | 0 | 0 | 0 | 15
TA Head / Leadership | 0 | 0 | 2 | 9 | 0 | 0 | 2 | 13
Oracle Team | 0 | 1 | 0 | 2 | 4 | 0 | 0 | 7
Vendors & Procurement | 0 | 0 | 1 | 0 | 7 | 0 | 0 | 8
AGS Marketing / Web | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2
Dev Team (Internal) | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 6
TOTAL | 7 | 6 | 16 | 20 | 14 | 5 | 4 | 72
Dependency List by Team and Category
Team | Category | Dep ID | Sprint | Dependency | Type | Owner | Required By | Status
AGS IT & Infra | Infrastructure | DEP-S1-01 | P5-S1 | SMTP server & email template engine configuration | External | AGS IT / Infra | Before 21-Sep | Not Started
AGS IT & Infra | Infrastructure | DEP-S1-05 | P5-S1 | Log table schema, storage sizing & retention policy | Internal | AGS DBA / Infra | Before 21-Sep | Not Started
AGS IT & Infra | Infrastructure | DEP-S4-02 | P5-S4 | Secure document storage with encryption (object store / DMS) | External | AGS Infra & Security | Before 02-Nov | Not Started
AGS IT & Infra | Infrastructure | DEP-S5-03 | P5-S5 | Recording storage capacity and retention policy | External | AGS Infra / Compliance | Before 16-Nov | Not Started
AGS IT & Infra | Infrastructure | DEP-S6-05 | P5-S6 | APM / monitoring tooling access (logs, traces, DB metrics) | External | AGS IT | Before 30-Nov | Not Started
AGS IT & Infra | Environment | DEP-S1-06 | P5-S1 | DEV and STG environments provisioned for Phase 5 | Internal | AGS IT / DevOps | Before 21-Sep | Closed
AGS IT & Infra | Environment | DEP-S1-12 | P5-S1 | Admin test accounts and sample user data on DEV/STG | Internal | AGS IT | Before 21-Sep | Not Started
AGS IT & Infra | Environment | DEP-S6-02 | P5-S6 | Production-like data volume for high-volume and 5x scalability testing | Internal | AGS DBA / IT | Before 30-Nov | Not Started
AGS IT & Infra | Environment | DEP-S6-03 | P5-S6 | Performance testing tool, licences and load environment | External | AGS IT / DevOps | Before 30-Nov | Not Started
AGS IT & Infra | Environment | DEP-S6-07 | P5-S6 | UAT environment with masked production-like data | Internal | AGS IT / DBA | Before 30-Nov | Not Started
AGS IT & Infra | Approval / Sign-off | DEP-S6-06 | P5-S6 | Infrastructure sizing confirmation for peak load | External | AGS Infra | Before 30-Nov | Not Started
AGS IT & Infra | Approval / Sign-off | DEP-S6-10 | P5-S6 | Change Advisory Board / release approval | Internal | AGS IT Governance | Before 30-Nov | Not Started
AGS IT & Infra | Approval / Sign-off | DEP-S6-11 | P5-S6 | Production deployment window and downtime approval | Internal | AGS IT / Business | Before 30-Nov | Not Started
AGS IT & Infra | Vendor / 3rd Party | DEP-S5-01 | P5-S5 | Kiosk photo capture hardware and SDK at interview locations | External | AGS IT / Facilities | Before 16-Nov | Closed
AGS IT & Infra | Vendor / 3rd Party | DEP-S5-02 | P5-S5 | Online interview platform - link generation and screenshot capability | External | AGS IT / Platform Vendor | Before 16-Nov | Not Started
AGS IT & Infra | Resource | DEP-S6-04 | P5-S6 | DBA support for indexing and query tuning | Internal | AGS DBA | Before 30-Nov | Not Started
AGS Security, Legal & Compliance | Infrastructure | DEP-S1-02 | P5-S1 | Email domain whitelisting (SPF / DKIM / DMARC) for candidate mails | External | AGS IT / Security | Before 21-Sep | Closed
AGS Security, Legal & Compliance | Infrastructure | DEP-S2-03 | P5-S2 | Secrets management / vault solution decision and provisioning | External | AGS Infra & Security | Before 05-Oct | Not Started
AGS Security, Legal & Compliance | Infrastructure | DEP-S2-04 | P5-S2 | Encryption key management (KMS) and key rotation policy | External | AGS Security | Before 05-Oct | Not Started
AGS Security, Legal & Compliance | Infrastructure | DEP-S5-10 | P5-S5 | External vendor user access model and email deliverability | External | AGS IT / Security | Before 16-Nov | Closed
AGS Security, Legal & Compliance | Approval / Sign-off | DEP-S2-06 | P5-S2 | Security team review of secret handling design | External | AGS Security | Before 05-Oct | Not Started
AGS Security, Legal & Compliance | Approval / Sign-off | DEP-S4-03 | P5-S4 | Data privacy, consent and retention approval for ID documents | External | AGS Legal / Compliance | Before 02-Nov | Not Started
AGS Security, Legal & Compliance | Approval / Sign-off | DEP-S5-08 | P5-S5 | Vendor document checklist and agreement templates | External | AGS Legal / Procurement | Before 16-Nov | Not Started
AGS TA Ops / BA | Data / Configuration | DEP-S1-03 | P5-S1 | Role, LOB and Location master data | Internal | AGS TA Ops | Before 21-Sep | Not Started
AGS TA Ops / BA | Data / Configuration | DEP-S1-10 | P5-S1 | Workflow state and transition catalogue per module | Internal | AGS TA Ops / BA | Before 21-Sep | Not Started
AGS TA Ops / BA | Data / Configuration | DEP-S2-01 | P5-S2 | Blacklist reason master list | Internal | AGS TA Ops | Before 05-Oct | Not Started
AGS TA Ops / BA | Data / Configuration | DEP-S2-05 | P5-S2 | Organizational approval hierarchy data (approvers by level and LOB) | Internal | AGS TA Ops / HR | Before 05-Oct | Not Started
AGS TA Ops / BA | Data / Configuration | DEP-S2-09 | P5-S2 | LOB / role to assessment mapping matrix | Internal | AGS TA Ops | Before 05-Oct | Not Started
AGS TA Ops / BA | Data / Configuration | DEP-S2-11 | P5-S2 | Voice Fresher Chennai restriction definition and role list | Internal | AGS TA Ops | Before 05-Oct | Not Started
AGS TA Ops / BA | Data / Configuration | DEP-S3-02 | P5-S3 | Stage-wise editable field matrix (post applicant creation) | Internal | AGS TA Ops / BA | Before 19-Oct | Not Started
AGS TA Ops / BA | Data / Configuration | DEP-S3-07 | P5-S3 | Interview slot / calendar master for Walk-In and Online modes | Internal | AGS TA Ops | Before 19-Oct | Not Started
AGS TA Ops / BA | Data / Configuration | DEP-S3-08 | P5-S3 | Sourcing channel master and ERS data feed | Internal | AGS TA Ops / ERS Owner | Before 19-Oct | Not Started
AGS TA Ops / BA | Data / Configuration | DEP-S3-09 | P5-S3 | Standard rejection reason master list | Internal | AGS TA Ops | Before 19-Oct | Not Started
AGS TA Ops / BA | Data / Configuration | DEP-S5-05 | P5-S5 | ORC ID master, panel and panelist master data | Internal | AGS TA Ops | Before 16-Nov | Not Started
AGS TA Ops / BA | Data / Configuration | DEP-S5-06 | P5-S5 | Interview location and panel calendar master | Internal | AGS TA Ops | Before 16-Nov | Not Started
AGS TA Ops / BA | Approval / Sign-off | DEP-S3-06 | P5-S3 | Six mapping scenario definitions (shared with Map Candidate) | Internal | BA / TA Ops | Before 19-Oct | Not Started
AGS TA Ops / BA | Approval / Sign-off | DEP-S4-10 | P5-S4 | Bulk Excel upload template format sign-off | Internal | TA Ops / BA | Before 02-Nov | Not Started
AGS TA Ops / BA | Approval / Sign-off | DEP-S5-12 | P5-S5 | Three end-to-end vendor test scenarios agreed | Internal | TA Ops / QA | Before 16-Nov | Not Started
TA Head / Leadership | Data / Configuration | DEP-S5-04 | P5-S5 | Competency framework and feedback form definitions | Internal | TA Head / HR | Before 16-Nov | Not Started
TA Head / Leadership | Data / Configuration | DEP-S5-11 | P5-S5 | Vendor performance KPI definitions | Internal | TA Head | Before 16-Nov | Not Started
TA Head / Leadership | Approval / Sign-off | DEP-S1-04 | P5-S1 | Signed-off RBAC permission matrix (role x object x action) | Internal | TA Head / Suresh | Before 21-Sep | Not Started
TA Head / Leadership | Approval / Sign-off | DEP-S1-07 | P5-S1 | IN-SCOPE (RBAC in, 4 items out) | Internal | Suresh Divakaran | Before 21-Sep | Closed
TA Head / Leadership | Approval / Sign-off | DEP-S1-11 | P5-S1 | Admin role definitions and hierarchy inputs | Internal | TA Head | Before 21-Sep | Not Started
TA Head / Leadership | Approval / Sign-off | DEP-S2-10 | P5-S2 | Cooling period rules sign-off (SHL 7/30/180, Versant 15/45/180) | Internal | TA Head / Suresh | Before 05-Oct | Not Started
TA Head / Leadership | Approval / Sign-off | DEP-S3-01 | P5-S3 | Final registration field list - mandatory vs optional | Internal | TA Head / BA | Before 19-Oct | Not Started
TA Head / Leadership | Approval / Sign-off | DEP-S4-04 | P5-S4 | Panelist photo verification process sign-off | Internal | TA Head / Compliance | Before 02-Nov | Not Started
TA Head / Leadership | Approval / Sign-off | DEP-S4-15 | P5-S4 | JD edit approval workflow definition (TA Head approval) | Internal | TA Head | Before 02-Nov | Not Started
TA Head / Leadership | Approval / Sign-off | DEP-S5-09 | P5-S5 | Vendor approval hierarchy sign-off | Internal | TA Head | Before 16-Nov | Not Started
TA Head / Leadership | Approval / Sign-off | DEP-S6-01 | P5-S6 | Report and KPI specification sign-off (funnel, vendor, recruiter) | Internal | TA Head | Before 30-Nov | Not Started
TA Head / Leadership | Resource | DEP-S6-08 | P5-S6 | UAT users nominated and available (TA, HR, Vendors) | Internal | TA Head | Before 30-Nov | Not Started
TA Head / Leadership | Resource | DEP-S6-12 | P5-S6 | Training schedule, trainer and training environment | Internal | TA Head / L&D | Before 30-Nov | Not Started
Oracle Team | Environment | DEP-S4-08 | P5-S4 | Test offer records and test candidates in the Oracle sandbox | External | Oracle Team | Before 02-Nov | Not Started
Oracle Team | Approval / Sign-off | DEP-S4-06 | P5-S4 | Oracle offer field mapping document sign-off | External | Oracle Team / TA Head | Before 02-Nov | Not Started
Oracle Team | Approval / Sign-off | DEP-S4-12 | P5-S4 | Oracle to DigiHire job field mapping sign-off | External | Oracle Team / BA | Before 02-Nov | Not Started
Oracle Team | Vendor / 3rd Party | DEP-S3-10 | P5-S3 | Oracle requisition validity feed (active vs expired jobs) | External | Oracle Team | Before 19-Oct | Not Started
Oracle Team | Vendor / 3rd Party | DEP-S4-05 | P5-S4 | Oracle Offer Interface - API spec, endpoints, credentials, sandbox | External | Oracle Team / AGS IT | Before 02-Nov | Not Started
Oracle Team | Vendor / 3rd Party | DEP-S4-07 | P5-S4 | Oracle status callback or polling mechanism agreement | External | Oracle Team | Before 02-Nov | Not Started
Oracle Team | Vendor / 3rd Party | DEP-S4-11 | P5-S4 | Oracle job requisition and LOB sync API + incremental change feed | External | Oracle Team | Before 02-Nov | Not Started
Vendors & Procurement | Data / Configuration | DEP-S5-07 | P5-S5 | Vendor master data, contracts and commercial targets | Internal | AGS Procurement / TA | Before 16-Nov | Not Started
Vendors & Procurement | Vendor / 3rd Party | DEP-S2-02 | P5-S2 | Vendor credentials issued - Versant, Oracle, ID Verification | External | Vendor Partners / AGS Procurement | Before 05-Oct | Not Started
Vendors & Procurement | Vendor / 3rd Party | DEP-S2-07 | P5-S2 | Versant API access and sandbox environment | External | Versant | Before 05-Oct | Closed
Vendors & Procurement | Vendor / 3rd Party | DEP-S2-08 | P5-S2 | Typing / other assessment tool API access | External | Assessment Vendor | Before 05-Oct | Closed
Vendors & Procurement | Vendor / 3rd Party | DEP-S3-04 | P5-S3 | Versant API availability (carried from P5-S2) | External | Versant | Before 19-Oct | Not Started
Vendors & Procurement | Vendor / 3rd Party | DEP-S4-01 | P5-S4 | External Identity Verification API - contract, credentials, rate limits | External | ID Verification Vendor / Procurement | Before 02-Nov | Not Started
Vendors & Procurement | Vendor / 3rd Party | DEP-S4-14 | P5-S4 | Buddy Finder platform access / API | External | Buddy Finder Owner | Before 02-Nov | Not Started
Vendors & Procurement | Vendor / 3rd Party | DEP-S6-09 | P5-S6 | Production credentials for all integrations - Oracle, Versant, ID Verification | External | Vendor Partners / AGS IT | Before 30-Nov | Not Started
AGS Marketing / Web | Data / Configuration | DEP-S3-03 | P5-S3 | Secure PDF template and branding for profile export | Internal | AGS TA / Marketing | Before 19-Oct | Not Started
AGS Marketing / Web | Vendor / 3rd Party | DEP-S4-13 | P5-S4 | Career Page publishing endpoint / CMS access | External | AGS Marketing / Web Team | Before 02-Nov | Not Started
Dev Team (Internal) | Predecessor Work | DEP-S1-08 | P5-S1 | Central logging framework delivered in week 1 of P5-S1 | Internal | Dev Team | By 25-Sep | In Progress
Dev Team (Internal) | Predecessor Work | DEP-S1-09 | P5-S1 | RBAC permission framework delivered in week 1 of P5-S1 | Internal | Dev Team | By 25-Sep | In Progress
Dev Team (Internal) | Predecessor Work | DEP-S2-12 | P5-S2 | Secrets vault delivered in week 1 of P5-S2 | Internal | Dev Team | By 09-Oct | Not Started
Dev Team (Internal) | Predecessor Work | DEP-S3-05 | P5-S3 | Email templates delivered in P5-S1 | Internal | Dev Team | Before 19-Oct | Not Started
Dev Team (Internal) | Predecessor Work | DEP-S4-09 | P5-S4 | 60-day score validity engine delivered in P5-S2 | Internal | Dev Team | Before 02-Nov | Not Started
Dev Team (Internal) | Resource | DEP-S6-13 | P5-S6 | Hypercare support roster and escalation matrix | Internal | PM / Dev Team | Before 30-Nov | Not Started

## Lists (hidden)
DevStatus | QAStatus | DeployStatus | Priority | Layer | DepStatus | DepType
Not Started | Not Started | Not Deployed | High | Frontend | Not Started | External
In Progress | In Progress | Ready for Deploy | Medium | Backend | Requested | Internal
Dev Complete | Passed | Deployed | Low | Full Stack | In Progress
Code Review | Failed | Verified |  |  | Available
Blocked | Re-Test | Deploy Failed |  |  | At Risk
On Hold | Blocked | Rolled Back |  |  | Blocked
Completed | Not Applicable | Not Applicable |  |  | Closed
Not Applicable